## EN
Stage/Time | Objective | Task | Expected Results
【0-1 month，Paris/Wenzhou】 （） preparation | 1. Prepare all necessary documents before the first formal meeting (hospital&CN&FR) | 1. Hospital use case definition 2. Sensor overview table and classification of all data types. 3. A work plan for the first phase. 4. Analysis of environmental and operational constraints of the hospital scenario. 5. Compilation of questions and discussion points for the upcoming meeting. | 1. Drafted use cases. 2. Sensor–data comparison table. 3. planning sheet. 4. Scenario analysis and question list for discussion.
【1-2 month，Wenzhou】 （） Paper + direction | 1. Read papers, build technical foundations. 2. Make sure about the research direction and scope for the next phases. | 1. Collect and read papers on indoor localization / ML / IoT / Data / Sensor / behavior analysis… organize them in Zotero. 2. Summarize the strengths and weaknesses of major indoor localization methods (KNN, DNN, CNN, GNN, etc.). 3. Identify the specific challenges and research questions related to hospital environments: RSSI noise, corridor topology, device interference, privacy constraints; summarize hospital-specific characteristics and their potential impact on localization models. 4. Adjust the research scope and methodology according to the actual conditions and constraints of the hospital. | 1. Papers notes and a technical knowledge map. 2. Defined preliminary research direction. 3. Updated research plan.
【2-4 month，Wenzhou】 （） prepare data collection + test | 1. Complete administrative and technical preparations for data collection. 2. Define accessible areas, required permissions, and device constraints. | 1. Determine the types of signals to be collected (Wi-Fi RSSI, BLE, UWB, etc.). 2. Discuss data collection requirements with the hospital, confirm accessible areas (draw a floorplan if needed). 3. Design the detailed data collection procedure (routes, point spacing, sampling duration). 5. Prepare hardware equipment Prepare hardware equipment (phones, BLE beacons, UWB nodes, etc.) and test device functionality and validate data collection apps/scripts. | 1. Hospital approval and collection authorization. 2. Fully prepared equipment and operational test environment.
【4-6 months，wenzhou】 （） optimize the collection + determine | 1. Validate the feasibility of the designed data collection workflow. 2. Finalize the complete data collection plan. | 1. Finalize all data types to be collected (Wi-Fi RSSI, BLE, UWB, IMU). 2. Refine the collection procedure (routes, point interval, repetitions). 3. Improve data logging scripts and collection tools. 4. Conduct small-scale trial collection (50–200 samples). 5. Fix workflow issues and optimize collection paths based on trial results. | 1. A validated and feasible data collection plan. 2. Trial dataset.
【6-12 month，wenzhou】 （） data collection + build dataset | 1. Complete large-scale data collection in the hospital environment. 2. Build a usable indoor localization dataset. | 1. Collect RSSI/BLE/UWB data across different areas (floors, rooms, corridors). 2. Create a coordinate system and define consistent labeling rules. 3. Perform data cleaning including filtering, denoising, and anomaly detection. 4. Standardize data structure into offline (training) and online (inference) sets. 5. Analyze variations caused by time or device differences. 6. Document metadata such as time, device type, and collection method. | 1. First usable version of the dataset. 2. Dataset description document.
【12-15 month，wenzhou】 （） baseline | 1. Build baseline models based on the collected dataset. 2. Establish unified evaluation metrics and error analysis procedures. | 1. Implement traditional ML baseline：KNN / SVM / Random Forest 2. Change some parameter to opyimize the result, such as DNN baseline（MLP regression）/ GNN baseline（GCN + k-NN graph）/ ... 3. Evaluate models：MAE / RMSE / Floor Accuracy 4. baseline behavior models | 1. Baseline experiment report. 2. Baseline error analysis report.
【15-18 month，wenzhou】 （） optimize model | 1. Complete training and evaluation of the traditional model. 2. Establish the foundation for the next innovation phase. | 1. Choose the best model direction and build the optimized first version. 2. Build the full prediction/evaluation pipeline and implement the code. 3. Compare parameter combinations and optimize model complexity. 4. behavior analysis models | 1. Initial model results. 2. Parameter optimization.

## CN
阶段/时间 | 目标 | 任务 | 预期成果 | 进度
【0-1月，巴黎/温州】 （） 准备工作 | 1. 整理第一次三方会议前的所需文档 | 1. 医院use case，RESP recovery case 2. 传感器对照表及数据类型 3. 对第一阶段做出计划 4. 分析场景限制 5. 整理会议问题/提问清单 | 1. Use case 初稿 2. 传感器/数据对照表 3. 计划表 4. 场景分析及文档 | 1. 11/13/2025 ISEP会1 2. 11/27/2025 ISEP会2 （注册Ing）
【1-2月，温州】 （） 文献调研+方向确认 | 1. 阅读文献积累技术基础 2. 定位后续研究方向及范围 | 1. 收集并阅读有关indoor localization / ML / IoT / Data / Sensor / 行为分析等的相关文献，建立Zotero库 2. 整理室内定位常用方法的优缺点整理对比 3. 确定医院环境的特定挑战及研究方向/问题：RSSI 噪声、走廊拓扑、设备干扰、隐私限制，总结医院场景特性与对模型的潜在影响 4. 结合医院实际情况做出调整 | 1. 文献笔记 / 技术图谱 2. 初步研究方向 3. 更新后续研究计划
【2-4月，温州】 （） 数据采集准备+试采集 | 1. 完成采集所需的行政、技术准备 2. 明确采集区域、权限及设备限制 | 1. 明确采集类型（Wi-Fi RSSI、BLE、UWB...）， 2. 与医院沟通采集需求，明确可采集区域，（如需要则绘制 hospital floorplan） 3. 设计详细数据采集流程（路线、点位间隔、采样时长） 4. 设备准备（手机、Beacon、UWB节点...） 5. 设备功能测试、APP/脚本验证 | 1. 医院审批确认/采集许可 2. 设备 + 可用实验环境
【4-6月，温州】 （） 小规模试采样+采集方案优化 | 1. 验证采集流程可行性 2. 确定完整的数据采集方案 | 1. 明确最终采集类型（Wi-Fi RSSI、BLE、UWB、IMU） 2. 设计采集流程（路线、点位间隔、采样时长、重复次数） 3. 优化采集脚本 & 记录工具 4.小范围试采样（50–200 条）验证可行性 5. 修复流程问题 & 优化采集路径 | 1. 可行的数据采集计划（数据类型/设备/路线） 2. 试采样数据
【6-12月，温州】 （） 数据采集与标注 建立可用数据集 | 1. 完成医院环境的大规模采集 2. 建立可用的室内定位数据集 | 1. 按区域采集 RSSI/BLE/UWB 数据（分楼层/科室/走廊） 2. 建立坐标系：走廊坐标、房间编号、楼层统一标注 3. 数据清洗：滤波、去噪、异常检测 4. 数据结构标准化：offline（训练）/online（推理）集合 5. 数据对比分析：不同时间/设备的差异 6. 文档化 metadata（时间、设备型号、采集方式） | 1. 初版可用数据集 2. 数据集描述文档
【12-15月，温州】 （） baseline构建 | 1. 基于数据集构建 baseline 模型 2. 建立统一评估指标与误差分析流程 | 1. 传统 ML baseline：KNN / SVM / Random Forest 2. DNN baseline（MLP regression）/ GNN baseline（GCN + k-NN graph）/ ... 3. 模型评估：MAE / RMSE / Floor Accuracy 4. Baseline行为分析模型 | 1. baseline 实验结果文档 2. baseline 误差分析报告
【15-18月，温州】 （） 初步定位模型构建+ 参数优化+技术尝试 | 1. 完成初版模型的训练与评估 2. 为后续阶段的创新研究奠定模型基础 | 1. 选择最佳模型方向，构建初版优化模型 2. 完整预测/评价流，并撰写代码 3. 对比参数组合，在复杂度方向进行优化 4. 融入行为分析方法 | 1. 初版模型结果 2. 参数优化记录